90-DAY FOUNDING CONVENING PLAN

The Next Chance Collaborative · From this week to a launched coalition

────────────────────────────────────────────────────────────

Goal

Convene 30-50 prospective member organizations and 5-10 individual influencers in a virtual + in-person hybrid Founding Roundtable in fall 2026 (target: October 2026). Walk out with at least 15 Confirmed Members publicly committed and named working-group chairs assigned.

Weeks 1–2 (now): Anchors first

Send personalized email or set a call with each of the 10 anchor organizations (see Anchor Members Shortlist).

Aim for 7+ verbal yeses by end of Week 2. Mark them as Invited in the dashboard.

Confirm a date for the Founding Roundtable. October weeks (Tue/Wed/Thu) work best; avoid the week before/after Thanksgiving.

Decide format: virtual-only (lower friction, scales), or hybrid (in-person + livestream — recommended). If hybrid, lock the venue.

Weeks 3–4: Charter and commitment doc

Finalize charter v1 (already drafted). Have anchors review and suggest edits.

Finalize one-page Member Commitment doc (see Member Commitment doc).

Stand up a placeholder landing page at thenextchancecollaborative.org with mission + names of confirmed anchors + 'Join us at the Founding Roundtable' RSVP link.

Build a save-the-date email and send to 30-50 warm prospects with anchor names attached.

Weeks 5–6: Working group leads named

Each anchor confirms whether they will chair a working group or co-chair.

For Action Tracks without an anchor (e.g. Housing, Family Comms), recruit a chair from the warm list — Together We Bake, GOSO, or LOHM are strong candidates for individual tracks.

Working group chairs draft a one-paragraph 'state of the field' for their track to share at the Roundtable.

Weeks 7–8: Secondary outreach push

Send formal invitations to the next 30-50 prospects (use the warm list filtered by 'Coalition Status: Prospect' and 'Temp: warm').

For each invitation, name two anchor organizations already confirmed.

Begin one-on-one calls with influencer/amplifier individuals (authors, podcasters) — ask for a soft commitment to mention TNCC at launch.

Update charter and landing page with new confirmed members weekly.

Weeks 9–10: Roundtable preparation

Finalize the Roundtable agenda (suggested: half-day; 25% strategy/charter, 50% working-group breakouts, 25% member spotlights + commitment moment).

Prepare member-spotlight one-pagers for the first 10 confirmed members (use Spotlight Template).

Send the funder pitch deck to 5-10 priority funders (see Funders category in dashboard) with a Roundtable invitation. Ask whether they'd attend as observers.

Press strategy: identify 3-5 outlets (Christianity Today, Sojourners, The Marshall Project, NextCity, local NPR) and offer an embargoed story about the launch.

Weeks 11–12: The Founding Roundtable

Hold the Roundtable. Members publicly commit (the 'Confirmed Member' moment).

Issue press release the day after, naming all founding members.

Update the dashboard, the public landing page, and send a launch email to all members.

Working groups schedule their first quarterly call within 30 days.

What 'success' looks like at Day 90

15+ Confirmed Members in the dashboard, with ≥1 each from Churches, Faith Networks, Reentry, Coaches, Returning-Citizen-led.

All 9 Action Tracks have a named chair (or co-chair).

Public landing page is live with founding member logos.

Press has covered the launch.

Working group call cadence is on the calendar.

First three funders have been pitched.

────────────────────────────────────────────────────────────

The hardest move is anchor #1. Make that call this week.